## PY6 Outfall Catchment Inventory
OF ID | OF Updated Priority | # of KJMHs in Catchment | # of KJMHs Visited | All KJMHs Complete? | IDs of KJ Inspected | Date(s) Visited | T&B Field Inspector | Other non-KJMH structures visited? | System Mapping Updates Needed? | Mapping Needs | Wet Weather Needed at this Outfall? (y/n) | Wet Weather Status | Date Visited | T&B Field Inspector | Reason to Investigate (SVF) | Wet Weather Sampling Results Summarized (individual results to be in separate tab) | Catchment Investigation Status | Revisit / Incomplete Notes
IC-4 | Interconnection | [9 empty] | no | [5 empty] | On Hold | Town stated that Boston Rd will be reconstructued by MassDOT next year and recommends holding off on investigation untill after new drainage is installed.
New_PPP | Low | 0 | 0 | N/A | N/A | 5/10/24 | Lauryn Patterson |  | yes | Field verification determined this was a duplicate of UNK-9 | N/A | [5 empty] | N/A Determined to be a duplicate of UNK-9
New-21 | Low | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson |  | yes | record drawing shows that this is a BMP outlet that connects to outfall OF_422 | no | [5 empty] | N/A Determined to be a BMP Outlet
New-CCC | Low | 0 | 0 | N/A | N/A |  |  |  |  | Confirmed TS by record drawing - ECO 5/8/24 | no | [5 empty] | Completed PY6
New-GGG | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes | confirmed connectivity between CB4440 and outfall | no | [5 empty] | Completed PY6
OF_10 | High |  |  |  | Unmapped MH | 4/16/2024 | Lauryn Patterson | Terminal structures | Yes - refer to mapbook markups and data issues | Screened at unmapped DMH that was at CB-1519 (CB-1531) location which collects flow from several unmapped CBs and drains to 2 unmapped DMH, then the final outfall point. CB1519 was also checked and only had one outlet pipe to the unmapped DMH. | Yes |  |  |  | 2” HDPE low pressure sewer crosses above a 12” drain line at the intersection of Main Street and Depot Road |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_1000 | Low | 2 | 2 | Yes |  | 4/20/2023 | Ellie Petraccione | Terminal structures | Additional inlet pipe observed at CB102 (GISID CB0099) leading to additional unmapped CB in the parking lot. That CB was determined to be the terminal structure. Upstream MH from MH67 has been paved over. Could not locate CB88 (terminal structure) due to storage containers blocking the structure. | No flow. Town needs to move a storage container in the back parking lot by CB88 in order to inspect terminal structure and complete catchment. PY6 - decided that Town provided sketch was sufficient for confirming remaining terminal structure | Yes |  |  |  | Town correspondences and comments indicate points where sewer crosses above drain. |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_1005 | Low | 0 | 0 | N/A | N/A | 5/21/24 | Lauryn Patterson | 0580 TS | no |  | no | [5 empty] | Completed PY6
OF_1016 | Low | 1 | 1 | Yes | 3231 | 5/5/23 5/2/24 | Anna Keimel Elizabeth Mitchell | Confirmed terminal structures 5/4/24 | No | Sampled and screened KJMH. Need to visit terminal structures to confirm complete. EVM Notes from 5/9 - "MH-3213 was confirmed as a terminal structure. We did not confirm the terminal structures for MH-3226 or UNK-37 because after completing them and using the iPad, I realized we had opened 3224." Revisited and confirmed terminal structures 5/4/24 | no | [5 empty] | Completed PY6
OF_1017 | Low | 0 | 0 | N/A | N/A |  |  |  | yes | Terminal structures confirmed by Town provided record plan Slight mapping update, see data issue layer | no | [5 empty] | Completed PY6
OF_1018 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | no | none | no | [5 empty] | Completed PY6
OF_1024 | Low | 0 | 0 | N/A | N/A | 5/21/24 | Lauryn Patterson | TS | no | none | no | [5 empty] | Completed PY6
OF_1040 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS and CB 1441 | no |  | no | [5 empty] | Completed PY6
OF_1043 | Low | 1 | 0 | no |  | 12/15/2023 | Lauryn Patterson | Yes - DMH-5362 and terminal structures | Yes - refer to mapbook markups | KJMH was buried. Opened DMH-5362 and confirmed that a pipe was going toward mapped KJMH location. Upstream DMH-5438 was paved over. CB1429 is connected to catchment | no | [5 empty] | Completed PY6
OF_1045 | Low | 0 | 0 | N/A | N/A |  |  |  | no | Town field verified mapping and TS. | no | [5 empty] | Completed PY6
OF_1056 | Low | 1 | 1 | no |  | 5/21/24 | Lauryn Patterson | TS | yes - see marked-up field mapbook | Significant mapping updates needed - see T&B field and Town mapbook CNL KJ DMH-5395 and CNO DMH-5396 Need to revisit | no | [5 empty] | Revisit | CNL KJ, need to inspect upstream structures
OF_1070 | Low | 0 | 0 |  |  | 5/3/24 | Evelyn Mortimer | CB 5431 | yes | Further mapping investigation needed. T&B field staff couldn't determine mapping. Couldn't confirm CB 5431 connectivity to outfall. | [6 empty] | Revisit | Need Town assistance to verify mapping Needs SVF review
OF_1071 | Low | 0 | 0 | N/A | N/A |  |  |  | No | Town field verfied mapping. | no | [5 empty] | Completed PY6
OF_1072 | Low | 0 | 0 |  |  | 5/3/24 | Evelyn Mortimer |  | yes | Further mapping investigation needed. T&B field staff couldn't determine mapping. | [6 empty] | Revisit | Need Town assistance to verify mapping Needs SVF review
OF_1092 | Low | 2 | 2 | yes | 0776 0742 | 5/2/24 5/21/24 | Elizabeth Mitchell Lauryn Patterson | MH0783, MH0773, MH0743, CB0758, MH0740, MH0788, MH073, MH0792 TS, 0798 and 0793 | Pipe connected all MHs inspected, following Depot Street. Unmapped MH located in front of 33 Depot Street. MH4862, MH4860, MH4861 DNE. | Unmapped CMP pipe enters MH0798, could not determine any upstream structures. 5/21/24 - Significant mapping changes needed. This drainage connects all the way down to Beaver Dam Drive. Able to confirm the terminal structures and included mapping updates in field markups. Screened DMH0798 it had high surfactants and chlorine results. Able to isolate flow (see markups). Crest Drive drainage does not connect to Depot Street. I did locate and screen an unmapped outfall that was located on Crest Drive. | no | [5 empty] | Completed PY6
OF_12 | Low | 0 | 0 | N/A | N/A | 5/2/24 | Elizabeth Mitchell | CB0610 | Yes - see data issue point | Mapping was investigated by Lauryn Patterson on 4/26. This area of Town has old drainage that runs parallel to newer drainage on Dunstable Road. The pipe networks join at CB0610. | no | [5 empty] | Completed PY6
OF_143 | Low | 0 | 0 | - | N/A |  |  |  | yes - see data issue point | Mapping and terminal structures confirmed by Town provided drawings | no | [5 empty] | Completed PY6
OF_16 | Low | 1 | 1 | yes | 4349 | 5/10/24 | Lauryn Patterson | yes - MH-4353 & TS | yes - see mapbook / data issue layer | Screened KJMH 4349; flow present but pipe was partially submerged so visited upstream structures. Sampled at MH-4353. Significant mapping changes needed - see mapbook. | no | [5 empty] | Completed PY6
OF_17 | Low | 0 | 0 | N/A | N/A | 5/10/24 | Lauryn Patterson |  | yes - see mapbook / data issue layer | OF_17 is an inlet that drains to the OF_16 catchment | no | [5 empty] | Completed PY6
OF_176 | High | 1 | 1 | yes | Unmapped MH | 4/16/2024 | Lauryn Patterson | Terminal structures | Yes - refer to data issues and mapbook markups from field day | Screened at unmapped DMH. Checked terminal structures. Drainage connects all the way up to Wayne Road | No | [5 empty] | Completed PY6
OF_178 | Low | 0 | 0 | N/A | N/A | 4/17/2024 | Lauryn Patterson | Terminal structures | Yes, refer to mapbook |  | no | [5 empty] | Completed PY6
OF_179 | Low | 1 | 1 | yes | 3970 | 4/24/24 | Lauryn Patterson | 3975 3968 - dry TS | Yes - refer to data issues and mapbook markups from field day | Flow present at KJMH 3970 i. High surfactants and chlorine from inletting pipes from DMH 3968 (0.75) and 3972 (0.5) ii. All upstream structures toward DMH 3968 were dry iii. Isolated high surfactants at DMH 3972 for that flow. | no | [5 empty] | Completed PY6
OF_18 | Low | 1 | 1 | no | 5570 | 5/10/24 5/21/24 | Lauryn Patterson | yes - 4346, 4345, Unmapped DMH & TS | yes - see field mapbook | Need detail to confirm TS on Carlisle Rd, I think MH5570 may end up be a KLJ depending on if more structures connect to CB5076 5/21/24 -determined that DMH-5570 should actually be the KJ but CNO - inspected upstream structures from both inlets in 5570 The unmapped manhole collects drainage coming from Diane Lane which is a private road. Visited first DMH on Diane Lane to confirm that it drained to the unmapped MH but did not visit additional structures on the road since it is private. | no | [5 empty] | Completed PY6
OF_189 | Low | 0 | 0 | N/A | N/A |  |  |  |  | Confirmed TS by record drawing - ECO 5/8/24 | no | [5 empty] | Completed PY6
OF_190 | Low | 0 | 0 | N/A | N/A |  |  |  |  | Confirmed TS by record drawing - ECO 5/8/24 | no | [5 empty] | Completed PY6
OF_20 | Low | 1 | 1 | yes | Unmapped CB | 5/3/24 5/21/24 | Evelyn Mortimer Lauryn Patterson | TS and new BMP | yes - see data issue layer and marked up field mapbook | new / unmapped CB found | no | [5 empty] | Completed PY6
OF_204 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes - see data issue layer | CNO MH5099, CB is terminal structure with small 4" PVC pipe. | no | [5 empty] | Completed PY6
OF_205 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes - see data issue layer | CNO MH5100, CB is terminal structure with small 4" PVC pipe. | no | [5 empty] | Completed PY6
OF_206 | Low | 1 | 1 | yes | 1842 | 12/15/23 | Evelyn Mortimer | All structures were visited in this catchment due to mapping errors and need to find flow direction | Yes, no inlet pipe from resident proprety into CB-1838, and OF from MH-1836 does not cross culvert. Pipe coming in to MH1895 is an inlet structure, all flow gooes towards OF-206. | Terminal structures confirmed. CB-1838 has no pipe from nearby property. KJCB-1837 has a 4" house inlet pipe from property. MH-1836 leads to a perpendicular inlet pipe. Refer to marked up mapbook (Group 4) in PY5 Catchment Investigations folder for more information. LEP revisited on 12/15/2023 and confirmed mapping that OF-208 acts as an outlet to a BMP structure. Terminal structures confirmed. | no | [5 empty] | Completed PY6
OF_212 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS and CB1926 | yes - see marked up mapbook | CB1926 screened – flow sampled from new unmapped MH Unmapped 12” HDPE pipe from CB off sidewalk | no | [5 empty] | Completed PY6
OF_216 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | no | none | no | [5 empty] | Completed PY6
OF_222 | Low | 1 | 1 | yes | 5641 | 5/18/23; Revisited 4/17/2024 | Evelyn Mortimer; Revisited by Lauryn Patterson | Terminal Structures | no | KJMH-5641 needs police detail due to busy street. KJMH screened on 4/17/2024. | no | [5 empty] | Completed PY6
OF_227 | Low | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson | TS | no |  | no | [5 empty] | Completed PY6
OF_229 | Low | 1 | 1 | yes | 4431 | 4/24/24 | Lauryn Patterson | TS | yes - see data issue layer / marked up mapbook | CB4731, DMH 5098, and DMH 5097 were not seen and assumed to be DNE, added data issue points for each DMH and CB. | no | [5 empty] | Completed PY6
OF_231A | Low | 0 | 0 | N/A | N/A | 5/2/24 | Elizabeth Mitchell | TS | no |  | no | [5 empty] | Completed PY6
OF_231B | Low | 1 | 1 | yes | 4444 | 5/2/24 | Elizabeth Mitchell | TS, MH4449 | yes - see data issue layer / marked up mapbook | OF is in correct location and MH4710 DNE. The pipe from MH4449 should go directly to OF. | no | [5 empty] | Completed PY6
OF_232 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes - see data issue layer | connectivity between CB4462 and outfall confirmed | no | [5 empty] | Completed PY6
OF_247 | Low | 0 | 0 | N/A | N/A | 5/10/24 | Lauryn Patterson | TS | yes - marked up field mapbook | Confirm connectivity between CB3009 and outfall Structures need to be shifted so they are on the road and not mapped in yard of house. | no | [5 empty] | Completed PY6
OF_251 | High | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson | TS | yes - marked up field mapbook | Only upstream structure appears to be the inlet pipe seen collecting flow from the quarry near #28 North Street. The mapped DMH the town noted does not collect flow from this pipe and does not drain to OF_251. It drains to the detention basin shown in the record drawings. I marked up the record drawings they provided based on what I saw in the field and screened the DMH. I did not see any other DMHs beside the terminal structures. | no | [5 empty] | Completed PY6
OF_255 | Low | 0 | 0 | N/A | N/A |  |  |  | No | Town field verified TS | no | [5 empty] | Completed PY6
OF_266 | High | 1 | 1 | yes | Unmapped CB | 4/26/24 | Lauryn Patterson | Terminal structures confirmed on 4/16 | yes - data issue / field mapbook / record drawings | Visited CB0008 area. Jeremy noted that morning this catch basin was installed as a cross drain. In the catchbasin I saw an inlet pipe coming from CB 0009 and an outlet pipe going across the street (based inlet/outlet on the pipe invert elevations). I took a photo of the catch basin (CB0008) and included it in the field mark ups. DMH 4977 and 4980 DNE | no | [5 empty] | Completed PY6 | Inspection of drainage that connects to OF_266 is complete but will need to investigate where CB0008 outlets too
OF_284 | Low | [9 empty] | no | [5 empty] | On Hold | Town stated that Boston Rd will be reconstructued by MassDOT next year and recommends holding off on investigation untill after new drainage is installed.
OF_290 | Low | 1 | 1 | yes | 2820 | 5/3/24 | Evelyn Mortimer | TS | yes - see data issue layer and marked up field mapbook | significant mapping issues and new outfall discovered | no |  |  |  | SVF review includes unmapped outfall next to OF_290 |  | Completed PY6
OF_307 | Low | 0 |  |  |  | 4/16/2024 | Lauryn Patterson | Yes terminal CBs | Mapping drawn in mapbook is accuate. | Confirmed that the only pipe leaving CB0549 is going toward outfall. No other pipes | no | [5 empty] | Completed PY6
OF_308 | High | 1 | 1 | Yes | 3034 2943 | 12/15/2023; Revisited 4/17/2024 | Lauryn Patterson |  | KJCB 3066 should not be key junction. KJCB 3067 should be added. There is a junction MH 3063, but do not think this is a key junction. | Significant mapping changes need to be made for this catchment. I initially sampled at CB-3879 before realizing the mapping errors. Afterward I sampled flow at the new KJ CB-2943. The CB also collects flow from a stream since a culvert passes through the CB, I did not sample the stream flow. Revisited and sampled at KJ CB3034. | no | [5 empty] | Completed PY6
OF_318 | Low |  | 0 | [5 empty] | yes - see data issue layer / record drawing | Terminal structures confirmed by Town provided record drawing | Yes |  |  |  | low pressure sewer system discharge point at the Abbot School as an area of concern for I/I |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_321 | High | 1 | 1 | yes | 2796 2793 | 12/8/23 | Evelyn Mortimer | All strucutres upstream of CB 2793 | Yes | CB 2793 has no manhole coming in from south inlet pipe. Inlet pipe comes in from CB-2796. CB-2796 has no manhole, it is going directly to CB2793. Dummy manholes at CB-5002, 5003, and 5004 do not exist. CB-5002 has 2" DI residential pipe coming in from house. CB-5003 has 12" corrugated metal pipe and 4"PVC coming in from woods. CB-5004 has inlet pipe coming from stream at newy mapped adta issue point. | no | [5 empty] | Completed PY6
OF_34 | Low | 1 | 1 | yes | 3078 | 4/20/2023 5/3/24 | Ellie Petraccione Evelyn Mortimer | Terminal structures, upstream CB 3300, upstream MH 3291 MH3295 | KJ structure is mapped as a CB, but is a MH. CB3298 (mapped as a terminal structure) had an additional connection and should be investigated by the Town. Two 4" pipes observed in MH3291 (flowing and sample collected). Return on 4/26/2023 to open MH3288 with WWO MH opener. | Slight sewage-like odor in KJMH and CB3291. Flow in KJMH from CB3291 above threshold values for surfactants and chlorine. Flow in upstream structure, CB3300, exceeded surfactants threshold and also had slight sewage-like odor. Flow in upstream structure, MH3291, originated from two 4" pipes located beneath the 12" inlet pipes. The 4" pipes were not mapped. Flow from 4" pipes exceeded surfactants and chlorine thresholds, but did not have a distinct odor. KJMH also had flow from MH3288. Could not open MH3288, opened the upstream structure (MH3285) which was dry. Confirmed terminal structures. We should revisit MH3288 and request Town opens this structure. Returned on 5/3/24 to inspect MH3295 (MH3288) | no |  |  |  | No sewer crossing per Town markups but there was a sewage odor during IDDE inspections EVR and ECO discussed on 5/6/24 and decided that odor was insufficient for wet weather screening. No SVF and No WWS |  | Completed PY6
OF_343 | Low | 0 | 0 | N/A | N/A |  |  |  | yes - see data issue layer | Terminal structures confirmed by Town provided record plan Slight mapping updates, see data issue layer | no | [5 empty] | Completed PY6
OF_346 | Low | 1 | 0 | No | 0638 | 6/1/2023 | Ellie Petraccione | MH 624, terminal structures | Yes - Appeared that CB 621 connected to MH 624, and CB 620 appeared to flow to CB 621. | CNL KJMH 4674, potentially paved over. Screened MH 624, dry. Confirmed terminal CBs 620, 625, and 626. CNL MH 4760, potentially paved over. Could not confirm outfall connection because MH 4762 was CNL. As per DPW and police detail, the intersection and drainage was recently redone. Town should investigate. | no | [5 empty] | Revisit - Drainage was recently updated and multiple manholes were CNL | Police Detail Required, need Town assistance to investigate mapping - pushed to PY7
OF_348 | Low | 0 | 0 | N/A | N/A |  |  |  | No | Town field verfied mapping and confirmed TS. | no | [5 empty] | Completed PY6
OF_349 | Low | 0 | 0 | N/A | N/A |  |  |  | yes - see data issue layer | Town field verfied mapping. See data issue layer for corrections | no | [5 empty] | Completed PY6
OF_368 | Low | 1 |  |  | 0626 |  |  |  | yes - see data issue layer | Town provided updated mapping. Determined CB0626 is a KJ and still needs to be inspected. | no | [5 empty] | Not started | SVF review complete but field work has not yet been started.
OF_369 | Low | 1 | 1 | yes | 3005 | 5/10/24 | Lauryn Patterson | TS | yes - see marked up mapbook | unmapped manhole present, added in markups and added data issue | no | [5 empty] | Completed PY6
OF_372 | High | 1 | 1 | yes | 2096 | 4/17/2024 | Lauryn Patterson | Terminal structures | No drainage pipe mapped to outfall need to update | Sampled at CB-2096 | no |  |  |  | Town's comment on SVF states unknown - industrial area Follow-up with Town on 5/23 stated No SVF |  | Completed PY6
OF_374 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes - see data issue layer | connectivity between MH5642 and outfall confirmed | no | [5 empty] | Completed PY6
OF_375 | High | 1 | 1 | yes | 128231 data point | 12/8/23 | Evelyn Mortimer | All strucutres visited in catchment. | Yes | New CB upstream of CB4552, with outlet pipe leading towards a new MH between CB and OF. MH sampled and flow screened. | No | [5 empty] | Completed PY6
OF_376 | Low | 0 | 0 | N/A | N/A | 5/3/24 | Evelyn Mortimer | TS | yes | connectivity between CB4466 and outfall confirmed | no | [5 empty] | Completed PY6
OF_383 | Low | 0 | 0 |  |  | 4/17/2024 | Lauryn Patterson | Terminal structures | Yes, refer to mapbook |  | yes |  |  |  | Town provided record plans that show point where sewer crosses above drain. |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_385 | Low | 0 |  |  |  | 4/17/2024 | Lauryn Patterson | Terminal structures | No |  | no | [5 empty] | Completed PY6
OF_386 | Low | 0 |  |  |  | 4/17/2024 | Lauryn Patterson | Terminal structures | Unmapped pipe leaving CB2317 directed toward OF_386. AT CB2316 there was an inlet 8" HDPE, could not locate where this was coming from. |  | no | [5 empty] | Revisit | Need to follow-up with Town to sort out mapping - pushed to PY7
OF_396 | Low | 0 | 0 | N/A | N/A | 5/10/24 | Lauryn Patterson | TS | no | Mapping appeared accurate to what is mapped. | no | [5 empty] | Completed PY6
OF_397 | Low | 1 | 1 | yes | 2006 | 5/10/24 | Lauryn Patterson | TS | yes - see marked up mapbook | Some mapping changes - the KJMH 2006 drains to the BMP system. See marked up mapbook from 5/10/24. | no | [5 empty] | Completed PY6
OF_406 | High | 2 | 2 | yes | 1794 New data point | 12/8/23 | Evelyn Mortimer | All terminal structures and all structures in circle | Yes | New structures added in multiple places. See mapbook for new manholes and pipes added | No | [5 empty] | Completed PY6
OF_409 | High | 1 | 1 | yes | 1810 | 4/27/2023 Revisit 4/24/24 | Emily Balcom Lauryn Patterson | Terminal structures 1811 | OF_409 is the actual MS4 OF point. OF_409A & OF_408 are both BMP structures. GIS should be updated accordingly. There is also an unmapped 4" PVC pipe entering CB2276 which appears to be coming from house #22. | OF_409 is the actual MS4 OF point. OF_409A & OF_408 are both BMP structures. BMP has significant green algal growth. House #13 has a large garden on a hill sloping down toward the BMP, so it's possible nutrients from fertilizer runoff could be contributing to algal growth. Homeowner also has chickens nearby and there appears to be a pump set up in the BMP to pump water from the BMP to water the garden. This was mentioned to the Town engineering staff at the end of the field day. REVISIT TO SCREEN MH - done | no | [5 empty] | Completed PY6
OF_41 | Low | 0 | 0 | N/A | 3086 | 4/20/2023 5/2/24 | Ellie Petraccione Elizabeth Mitchell | Terminal structures CB-3085 | CB3295 is mapped as a terminal structure but has an inlet pipe. CB3306 is a MH and CB3306 had two additional inlet pipes that were unmapped. Appears that CB3306 is a potential KJMH with flow from CB3297 system, CB3305, and CB3307 before discharging to OF. | CB3305 and CB3307 were observed to be terminal structures. Confirmed OF_39 is BMP inlet and OF_41 is outfall. REVISIT TO COMPLETE DW MH INSPECTION Revisited on 5/2 to inspect CB-3085 (technically MH) Mapping unclear if this was key junction or not, inspected to be safe | Yes |  |  |  | Crossing between sewer force main and drain where drain is below sewer. See Rita Miller school mapbook for drawings provided by the Town. |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_421 | Low | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson |  | yes | record drawing shows that this is a BMP inlet that is apart of OF_422 system | no | [5 empty] | N/A Determined to be a BMP Inlet
OF_422 | Low | 1 | 1 | yes | 4135 | 4/24/24 | Lauryn Patterson | TS | yes - see data issue layer | Town provided record drawings that was accurate to what was seen in the field. DMH-4128 that is mapped in AGOL is a sewer manhole. | no | [5 empty] | Completed PY6
OF_423 | Low | 1 | 1 | yes | 4625 | 12/8/23 | Evelyn Mortimer | yes, terminal structures | Yes, see at right | Terminal structures confirmed KJMH-4635 screened, flow coming from MH-4627, MH-4672, and and CB-4624. Basin sampled, all flow under levels MH-4644, 4643, and 4642 all connected. MH-4644 and 4642 both have 8" SDR drains from pipe, both have clear flow and most likely from house AC systems. | Possible Update 1/18/24 - Yes SVF |  |  |  | Reviewed Hitchin Post Greens As-built and Sewer System plans - sewer is above drain in some parts of Chicory Rd. Appears to be 2 points with sewer-drain crossing and sewer is above the drain. Yes SVF |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_424 | Low | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson | TS | yes - see data issue layer |  | yes |  |  |  | Town provided record plans that show point where sewer crosses above drain. |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
OF_430 | Low | 1 | 1 | yes | 4556 | 4/24/24 | Lauryn Patterson | Confirmed terminal structures. | yes - see data issue layer & marked up mapbook | Confirmed that DMH 4652 drains to OF_428 (Lewis said they had previously filmed this pipe) Confirmed that DMH 4559 drains to OF_429 (Lewis said they had previously filmed this pipe)No flow present at KJMH 4556 | Unknown Update 3/19/24 - No SVF |  |  |  | Review of Hitchin Post Greens as-built and sewer system plans show sewer below drain along "Howard Rd" (Location referred to as Howard Rd on plans from 1988 but it appears that since then it was remained to Magnolia Rd |  | Completed PY6
OF_451 | High | 0 | 0 | N/A | N/A | 4/16/24 | Lauryn Patterson | TS | significant mapping updates, see data issue points | Confirmed terminal structure - only connecting structure owned by Town. The remaining drain structures are on a private road | No | [5 empty] | Completed PY6
OF_455 | High | 0 | 0 | N/A | N/A | 5/10/24 5/21/24 | Lauryn Patterson | TS MH2537 MH2622 | yes - significant mapping updates | See data issue points and marked-up field mapbook Could not locate inlet headwall/pipe coming from end of Tavern Circle. We searched the woods and the nearby front yards but did not see a structure that is mapped in the record drawings | No | [5 empty] | Revisit | Inlet structure shown on record drawing couldn't be located in field
OF_469 | Low | 1 | 1 | yes | 2906 | 4/17/2024 | Lauryn Patterson | Terminl structures | Yes, refer to map book markups |  | no | [5 empty] | Completed PY6
OF_471 | Low | 0 | 0 | N/A | N/A | 4/17/2024 | Lauryn Patterson | Terminl structures | Yes, refer to map book markups |  | no | [5 empty] | Completed PY6
OF_5 | High | 0 | 0 | N/A | N/A | 5/2/24 | Elizabeth Mitchell | Yes, terminal CBs and CB0601 and CB0602 | Yes - Unmapped MH observed connected to CB0601 and CB0602 | CB0603 is terminal and is not connected to catchment OF-12. Two HDPE pipes enter CB0597 and no upstream structures were identified. | no | [5 empty] | Completed PY6
OF_544 | Low | 0 | 0 | N/A | N/A |  |  |  | yes - see data issue layer | Terminal structures confirmed by Town provided record plan Slight mapping updates, see data issue layer | no | [5 empty] | Completed PY6
OF_545 | Low | 0 | 0 | N/A | N/A |  |  |  | no | Terminal structures confirmed by Town provided record plan | no | [5 empty] | Completed PY6
OF_549 | Low | 0 | 0 | N/A | N/A |  |  |  | no | Town provided record plan indicates this is a BMP structure | no | [5 empty] | N/A Determined to be a BMP structure
OF_551 | Low | 0 | 0 | N/A | N/A |  |  |  | no | Terminal structures confirmed by Town provided record plan | no | [5 empty] | Completed PY6
OF_552 | Low | 0 | 0 | N/A | N/A | 2023-04-19 | Anna Keimel | both terminal MHs and CBs | OF 553 potential DNE could not find | Could not find suspected BMP outlet, only inlet. | no | [5 empty] | Completed PY6
OF_563 | Low | 0 | 0 | N/A | N/A |  |  |  | no | TS confirmed by record drawings | no | [5 empty] | Completed PY6
OF_568 | Low | 0 | 0 | N/A | N/A |  |  |  | no | TS confirmed by record drawings | no | [5 empty] | Completed PY6
OF_581 | Low | 0 | 0 | N/A | N/A |  |  |  | yes - see data issue layer | Terminal structures confirmed by Town provided record plan Slight mapping updates, see data issue layer / record plan | no | [5 empty] | Completed PY6
OF_6 | Low | 1 | 1 | yes | 1806 | 12/15/23 | Evelyn Mortimer | MH 1802, MH1806, unnamed MH on Oak and Poplar Road, unnamed MH downstream of MH1819 on Maple Road, TS, KJMH 4755 | yes | Could not open KJMH, MH4909, or JMH on Poplar near CBs 1798 and 1799. Confirmed all terminal structures except drainage at Poplar and Plain Road, which had indications of new drainage (newly asphalted lines leading to CB 1224 and CB7. KJMH returned to on 5/5/23, screened and dry. REVISIT TO SCREEN KJMH AT THE INTERSECTION OF HEMLOCK ROAD AND ELM STREET LEP revisited on 12/15/2023 Flow screeened and sampled at MH1806. No structure present at Elm Road and Hemlock Road. | no | [5 empty] | Completed PY6
OF_7 | Low | 1 | 1 | Yes | 1714 1710 | 12/15/2023; Revisited 4/17/2024 | Evelyn Mortimer | Terminal CBs, plus upstream structures from KJMH |  | Could not locate KJMH, buried in woods. Went to upstream structure. Sampled from upstream MH. Elevated Surfactants. Sampled next upstream CB with tricklet of flow. Elevated surfactants. Could not trace flow. All remaining upstream strucutres had standing water, but below inverts. JCB screened, but terminal structures need to be confirmed once construction is over. REVISIT TO CONFIRM TERMINAL STRUCTURES ON PLAIN ROAD - REQ. DETAIL (CB1734, CB 1774, CB 1674, and MH connecting CB 1358 and CB 1357) LEP Revisited on 12/15/2023 and confirmed terminal structures CB1713, 1732, and 5376. CNL MH-5371 appears to be buried. DPW attempted to locate but it could not be found at time of inspections. Visited on 4/16/24 and 4/17/2024 sampled at CB-1710 and found high results on 4/16. Revisited on 4/17 to isolate source. At CB 1710 a house had a hose leaving that drained into the basin from their driveway. This appeared to be the source of flow. Sampled flow leaving 1713 and entering CB1714 and it had 0.5 mg/L of Surfactants. | no | [5 empty] | Completed PY6
OF_83 | Low | [7 empty] | yes | No connecting structures mapped. Record drawing provided by Town didn't show connection. Will need to field investigate mapping. | Yes |  |  |  | low pressure sewer system discharge point at the Abbot School as an area of concern for I/I |  | Not started | Priority for PY7 investigations
OF_85 | Low | 0 | 0 | [6 empty] | Town provided mapping/as-built. Outfall appears to be part of a twin culvert used for parking lot drainage. No structures connected to it. | Yes |  |  |  | Old septic pipe crosses above these drain pipes, see Roudenbush Septic Plan. |  | Incomplete - Needs WWS No CI needed PY6 | Needs Wet Weather Screening
OF_86 | Low | 0 | 0 | [6 empty] | Town provided mapping/as-built. Outfall appears to be part of a twin culvert used for parking lot drainage. No structures connected to it. | Yes |  |  |  | Old septic pipe crosses above these drain pipes, see Roudenbush Septic Plan. |  | Incomplete - Needs WWS No CI needed PY6 | Needs Wet Weather Screening
UNK-45 | Low | 0 | 0 | N/A |  | 4/27/2023 | Emily Balcom | Terminal CB | No | Mapping is correct. Stagnant pool in terminal CB. | no | [5 empty] | Completed PY6
UNK-47 | Low | 0 |  |  |  | 4/17/24 | Lauryn Patterson | Confirmed terminal structures |  |  | no | [5 empty] | Completed PY6
UNK-49 | Low | 0 |  |  |  | 4/17/24 | Lauryn Patterson | Mapped BMP structure. Took photos of the area and saved in the mapbook. | Review mapbook to determine - could not locate some structures in the field. |  | no | [5 empty] | Completed PY6
UNK-55 (BMP Inlet) and UNK-56 (Outfall) | Low | 1 | 1 | yes | 4120 | 12/15/23 | Evelyn Mortimer | Terminal CBs. BMP outlet structure and outlet OF | Yes - UNK-56 is the correct outfall. | Correct outfall - UNK-55 is BMP inlet. UNK-56 screened in PY3, can be considered complete. Flow coming into JMH4182 and KJMH 4194 both too deep to sample. (12' and 16' deep). Screen KJMH 4194 to check if dry. Needs double-pole to sample since it is 16'. LEP Revisited on 12/15/2023 and sampled flow with ammonia test strips. | Possible Update 1/31/24 - Yes SVF |  |  |  | Reviewed as-builts and found one spot where sewer & drain cross and the sewer is above the drain. Yes SVF |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
UNK-59 | Low | 1 | 1 | yes | 2071 | 5/20/24 | Lauryn Patterson | TS | no | town provided record drawings in GIS | no | [5 empty] | Completed PY6
UNK-60 | Low | 0 | 0 | N/A | N/A |  |  |  |  | Confirmed TS by record drawing - ECO 5/8/24 | no | [5 empty] | Completed PY6
UNK-66 | Low | 0 | 0 | N/A | N/A | 5/2/24 | Elizabeth Mitchell | yes - unmapped inlets/outlets | yes - see town mark ups & data issue layer | significant mapping corrections needed - new outfalls will need to be added No KJ for this outfall TS were confirmed via Town provided drawings/markups | no | [5 empty] | Completed PY6
UNK-67 | Low | 1 | 1 | yes | 3931 | 4/26/24 | Lauryn Patterson | TS | yes - see town mark ups & data issue layer |  | no | [5 empty] | Completed PY6
New4.26_1 | [8 empty] | yes | New outfall located during PY6 investigations | [6 empty] | Not started | Located during PY6
New4.26_2A | [9 empty] | New outfall located during PY6 investigations Appears to be BMP structure | no | [5 empty] | Completed PY6
New4.26_2B | [8 empty] | yes | New outfall located during PY6 investigations | no | [5 empty] | Not started | Located during PY6
New4.26_3 |  | 1 | 1 | yes | 0572 | 4/26/24 | Lauryn Patterson | TS | yes - see data issue layer & record drawings | New outfall located during PY6 investigations | no | [5 empty] | Completed PY6
New4.26_4 |  | 0 | 0 | N/A | N/A | 4/16/24 | Lauryn Patterson | TS | yes | New outfall located during PY6 investigations | no | [5 empty] | Completed PY6
New.4.26_5 | [8 empty] | yes | New outfall located during PY6 investigations | [6 empty] | Not started | Located during PY6
New4.26_6 | [8 empty] | yes | New outfall located during PY6 investigations | [6 empty] | Not started | Located during PY6
New4.24 |  | 0 | 0 | N/A | N/A | 4/24/24 | Lauryn Patterson | TS | yes - see data issue point | Opened DMH 4097 and found the outfall pipe. Added data issue at outfall location with picture of outfall. Confirmed terminal structures CB-4101, CB-4103, and DMH-4102. No key junction present but will need to follow up with Town if an SVF has been recorded in this area. | yes |  |  |  | Development has a wasterwater collection system in the road that connects to a common septic. Hitch Green plans show crossing point between sewer and drain where sewer is above drain on Magnolia Dr |  | Incomplete - Needs WWS DW CI Completed in PY6 | Needs Wet Weather Screening
New5.13 | TBD | [7 empty] | yes | New outfall located during PY6 investigations | [6 empty] | Not started | Located during PY6
New5.21 | TBD | [7 empty] | yes | New outfall located during PY6 investigations | [6 empty] | Not started | Located during PY6

## Catchment Inspection Data
ObjectID | GlobalID | CreationDate | Creator | EditDate | Editor | Catchment Outfall ID | Catchment Outfall Location | Manhole ID / Catch Basin ID | Manhole / Catch Basin Location | Junction? | Key Junction? | Todays Date/Time | Investigators | Other - Investigators | Temperature (F) | Rainfall (In) Last 72 Hours | Rainfall (In) Last 24 Hours | Maintenance Needs | Other - Maintenance Needs | Inverts Submerged? | If yes, which pipe? | Flow Present? | Flow Description | Flow Source | Intermittent flow trap (e.g., sandbag recommended) recommended? | Surfactants (>0.25 mg/L) Result | Ammonia (NH3)(>0.5 mg/L) Result | Chlorine (>0.02 mg/L) Result | Evidence of a potential illicit discharge/connection? | Explanation | Odor | Odor Description | Other - Odor Description | Floatables (Does not include trash) | Floatable Description | Other - Floatable Description | Notes | GIS ID | System mapping updates needed? | Yes - System mapping updates needed? | Field Questions | x | y
89 | 93442192-703e-4bcb-8b88-4c5b96ef8c1d | 2023-12-08 13:34 | EthanManley | 2024-05-28 18:43 | EOlsonTB | OF-206 | Landmark Rd | MH-1842 | Landmark Rd | Yes | Yes | 2023-12-08 13:00 | other | Evelyn Mortimer | 25 | 0.01 | 0 |  |  | No |  | Yes | Trickle | Pipe from north flowing into OF pipe, pipe flowing from south into OF pipe | No | 0.25 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  | Flow going into OF-206 pipe. |  | No |  |  | -71.3942 | 42.5394
90 | 517f8dd2-8773-48b4-8362-582c8fcfdf4e | 2023-12-08 14:47 | EthanManley | 2024-05-28 18:42 | EOlsonTB | OF-375 | Overlook Dr | 128231 | Overlook Dr | No | No | 2023-12-08 14:11 | other | Evelyn Mortimer | 28 | 0 | 0.01 |  |  | No |  | Yes | Trickle | Unmapped CB upstream of CB4552 | No | 0.25 | 0.25 | 0.1 | Unlikely |  | No |  |  | No |  |  | Unmapped manhole, BMP inlet. Point added as data issue 128231 for new manhole to be added. |  | No |  |  | -71.405 | 42.5479
91 | dc792639-c753-47eb-8c3a-365e02f1520f | 2023-12-08 15:49 | EthanManley | 2024-05-28 18:42 | EOlsonTB | OF-321 | Court Rd | CB-2793 | Court Rd | Yes | Yes | 2023-12-08 15:00 | other | Evelyn Mortimer | 30 | 0.01 | 0 |  |  | No |  | Yes | Substantial | CB 2796 flows into CB, dummy manholes do not exist. | No | 0.5 | 0.25 | 0.08 | Potential | Surfactants hit | Yes | Rancid/sour |  | No |  |  |  |  | other |  | Dummy manhole does not exist. CB has inlet pipe coming from CB 2796. | -71.4299 | 42.5784
92 | 35fc7241-6bfa-4049-8625-74ecae46c6e1 | 2023-12-08 17:04 | EthanManley | 2024-05-28 18:42 | EOlsonTB | OF-321 | Court Rd | CB-2796 | Crown Rd | No | No | 2023-12-08 16:35 | other | Evelyn Mortimer | 32 | 0.01 | 0 |  |  | No |  | Yes | Substantial | CB-2795 | No | 0.25 | 0.25 | 0.09 | Unlikely | No signs of illicit discharge. | No |  |  | No |  |  |  |  | other | Dummy manhole does not exist. CB flows into 2793 |  | -71.4314 | 42.5786
93 | e7fb8ca7-c71e-47d0-88f1-cebb113046ac | 2023-12-08 17:13 | EthanManley | 2023-12-08 17:13 | EthanManley | OF-406 | Starr Circle | New data point | Starr Circle | No | No | 2023-12-08 17:10 | other | Evelyn Mortimer | 35 | 0.01 | 0 |  |  | No |  | No | [6 empty] | Unlikely | [9 empty] | other | New unmapped structure. Pipe direction on data issue point |  | -71.456 | 42.5747
94 | 1d07881b-f6ba-491f-b264-4e22b1664ba3 | 2023-12-08 18:19 | EthanManley | 2024-05-28 18:42 | EOlsonTB | OF-406 | Starr Circle | MH-1794 | Starr Cir | No | No | 2023-12-08 17:52 | other | Evelyn Mortimer | 35 | 0.01 | 0 |  |  | No |  | Yes | Substantial | Unmapped MH in driveway | No | 0.25 | 0.25 | 0.02 | Unlikely |  | No |  |  | No |  |  |  |  | other | See data issue points |  | -71.4556 | 42.5748
95 | 3a54f7cc-364a-440d-a010-d5e7b9b15be0 | 2023-12-08 19:12 | EthanManley | 2023-12-08 19:12 | EthanManley | OF-423 | Chicory Lane | MH-4625 | Chicory Ln | Yes | Yes | 2023-12-08 18:29 | other | Evelyn Mortimer | 45 | 0.01 | 0 | other |  | No |  | Yes | Substantial | Flow from CB-4624 and two manhole inlets | No | All in notes - three inlets flowing |  |  | Unlikely |  | No |  |  | No |  |  | From CB 4624: am-.25 cl- 0 sf- .25 From MH 4672: am .25 cl 0 sf- .25 From MH 4627: am .25 cl .03 sf- .25 |  | No |  |  | -71.4695 | 42.5563
96 | d9f0ffd0-3fc7-4f3b-86ae-b21fcf6103ab | 2023-12-08 19:43 | EthanManley | 2024-05-28 18:41 | EOlsonTB | UNK-56 | Casie Ln | MH4120 | Casie Ln | Yes | Yes | 2023-12-08 19:16 | other | Evelyn Mortimer | 40 | 0.01 | 0 |  |  | No |  | Yes | Trickle | MH4117 | No | 0.25 | Need to return to complete ammonia | 0 | Unlikely | [7 empty] | Need to return to complete ammonia test. |  |  |  |  | -71.4651 | 42.5539
97 | 04f921c3-a44a-4dbe-8886-72a0c3efb601 | 2023-12-15 14:02 | LaurynPatterson | 2023-12-15 14:02 | LaurynPatterson | Test | Test |  |  | No | Yes | 2023-12-15 14:01 | other | LP |  |  |  | Pipe_blockage |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  |  | other |  |  | 0 | 0
98 | df804677-14b9-4666-8702-a17943e979cc | 2023-12-15 14:50 | LaurynPatterson | 2024-05-28 18:41 | EOlsonTB | OF_6 | Hemlock Road | DMH-1806 | In front of #16 Hemlock | Yes | No | 2023-12-15 14:26 | other | Lauryn Patterson | 40 | 0 | 0 |  |  | No |  | Yes | Moderate | Pipe 1157 | No | 0.25 | 0 | 0.06 | Unlikely |  | No |  |  | No |  |  |  |  | other | Could not view DMH-1763 |  | 0 | 0
99 | 6296b6b5-838a-4cc9-8b76-131cb2ae93f5 | 2023-12-15 16:14 | LaurynPatterson | 2023-12-15 16:14 | LaurynPatterson | of-571 | Cutter Lane | DMH-4277 | Cutter Lane x True Bean Way | Yes | Yes | 2023-12-15 15:19 | other | Lauryn Patterson | 40 | 0 | 0 |  |  | No |  | Yes | Trickle | Pipe-1541 | No | 0.25 | 0 | 0.02 | Unlikely |  | No |  |  | No |  |  |  |  | No |  |  | 0 | 0
100 | 839bcbf3-a20b-4ce1-8ae3-4bb2fc54c77c | 2023-12-15 19:16 | LaurynPatterson | 2024-05-28 18:43 | EOlsonTB | OF-308 | Fletcher Road | CB-2943 | Fletcher Road | Yes | Yes | 2023-12-15 19:07 | other | LP | 50 | 0 | 0 | Structure_damage/corrosion |  | No |  | Yes | Moderate | Pipe 2006 | No | 0.25 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  |  |  | other | Refer to map book |  | 0 | 0
101 | d0855c3a-874d-4252-8d2c-f535d181dd37 | 2023-12-18 13:40 | LaurynPatterson | 2023-12-18 13:40 | LaurynPatterson | UNK-56 | End of Casie Lane | MH-4120 | Casie Lane x Greenbrier Drive Intersection | Yes | Yes | 2023-12-18 13:29 | other | Lauryn Patterson | 40 | 0 | 0 |  |  |  |  | Yes | Moderate | Pipe 4125 and Pipe 3145. | No | N/A | 0.25 | N/A | Unlikely | Pipe 3145 and Pipe 4125 had flow and were sampled for ammonia both had ammonia levels of 0.25. | No |  |  | No |  |  | Returned from 12/8/23 screening to complete ammonia test. |  | No |  |  | 0 | 0
102 | a3488672-6569-4990-93bf-6785149699fc | 2024-04-16 11:59 | LaurynPatterson | 2024-04-22 00:15 | EOlsonTB | OF_372 | Bridge Street | 2096 | Bridge Street | No | No | 2024-04-16 11:55 | other | LP | 44 | 0.05 | 0 |  |  | No |  | Yes | Moderate | Upstream CB 2095 | No | 0.25 | 0.25 | 0 | Unlikely |  | No |  |  | No |  |  |  | {F58B40F3-30EF-4A07-9525-19EBA0E5DCB7} | other | CB 2096 collects drainage from CB-2095 then outfalls into woods |  | -71.4614 | 42.5913
103 | 550e425e-a7b7-44e7-bcca-ff6e35830f89 | 2024-04-16 14:22 | LaurynPatterson | 2024-05-03 12:01 | EOlsonTB | OF_10 | Main Street | Unmapped DMH | Main Street | Yes | Yes | 2024-04-16 13:03 | other | Lauryn Patterson | 55 | 0.05 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  |  | other | See data issue layer. | Unmapped DMH, collects flow from CB 1531,1521, and unmapped catchbasin. | -71.4354 | 42.584
104 | 4c86206c-2268-4a22-8614-5248e374b3f0 | 2024-04-16 14:22 | LaurynPatterson | 2024-04-22 00:15 | EOlsonTB | OF_176 | Wagon Trail Road | Unmapped DMH | Old Lowell Rd x Wagon Trail Road | Yes | Yes | 2024-04-16 14:04 | other | Lauryn Patterson | 60 | 0.05 | 0 |  |  | Partially | Pipe from CB 4363 and DMH 5088. Confirmed no flow at DMH 5088. | Yes | Moderate | CB 4363 | No | 0.25 | 0.25 | 0 | Unlikely |  | No |  |  | No |  |  |  |  | other | Sampled at KJMH that was not mapped in AGOL, inspected based on record drawings. |  | -71.4121 | 42.5531
105 | 3348e2f5-fadf-46c8-b2c8-71a13ac6f8be | 2024-04-16 21:06 | LaurynPatterson | 2024-04-17 11:51 | EOlsonTB | OF_7 | Woodbine Terrace | 1710 | Woodbine Terrace | Yes | No | 2024-04-16 18:02 | other | Lauryn Patterson | 65 | 0.05 | 0 |  |  | No |  | Yes | Moderate | Pipe GIS1487 and 1436. Flow also coming from house sump pump. Survey is for flow CB1708. | No | 0.25 | 0 | 0.09 | Unlikely |  | No |  |  | No |  |  |  | {B47D38C0-0CD2-4038-84A0-FD409670AB15} |  |  |  | -71.4195 | 42.6125
106 | 39ca2132-71e7-4a8f-b9c8-519858820ab8 | 2024-04-16 22:28 | LaurynPatterson | 2024-04-16 22:29 | LaurynPatterson | OF_7 | Woodbine Terrace | 1710 | Woodbine Terrace | Yes | No | 2024-04-16 18:02 | other | Lauryn Patterson | 65 | 0.05 | 0 |  |  | No |  | Yes | Moderate | Pipe GIS1487 and 1436. Flow also coming from house sump pump. Survey is for flow from CB1711. | No | 0.5 | 0.5 | 0.08 | Potential | High surfactants and ammonia | No |  |  | No |  |  |  | {B47D38C0-0CD2-4038-84A0-FD409670AB15} | No |  |  | -71.4195 | 42.6125
107 | 5df21b5d-25f1-4bc4-a225-fa788320a4ac | 2024-04-17 12:23 | LaurynPatterson | 2024-04-22 00:15 | EOlsonTB | OF_7 | Woodbine Terrace | 1714 | Torrington Avenue | No | No | 2024-04-17 12:04 | other | Lauryn patterson | 44 | 0.04 | 0 |  |  | Partially | GIS ID 1434 | Yes | Trickle | Flow coming from CB1713, pipe GISID 1433. Flow entering catchbasin CB1713 is from sump pump drain | No | 0.5 | 0 | 0.02 | Potential | Sump pump draining from house #5 Torrington Ave | No |  |  | No |  |  | Photo 1 is of sump pump drain coming from house to CB1713. | {E2FE4675-DCE5-4A16-9C80-D9674BB79FE9} | No |  |  | -71.4184 | 42.613
108 | 831d032b-26c4-47ec-a42a-8dfea99a609e | 2024-04-17 13:22 | LaurynPatterson | 2024-04-17 13:22 | LaurynPatterson | OF_308 | Fletcher Road | 3034 | Beaver Dam Drive | Yes | Yes | 2024-04-17 13:07 | other | Lauryn Patterson | 47 | 0.04 | 0 |  |  | No |  | Yes | Substantial | Flow from CB3037, CB3035, and CB3033. this survey is for flow from CB3037. | No | 0.25 | 0.25 | 0.01 | Unlikely |  | No |  |  | No |  |  | Drain from house is also present in CB. | {C61A9C7D-F01B-4685-8E8A-A44803AC282E} | other | No manhole drains to CB, this is just a house drain |  | -71.438 | 42.5903
109 | 896f9ec8-2340-4cab-bc98-3466f5eb76e0 | 2024-04-17 13:42 | LaurynPatterson | 2024-04-17 13:42 | LaurynPatterson | OF_308 | Fletcher Road | 3034 | Beaver Dam Drive | Yes | Yes | 2024-04-17 13:07 | other | Lauryn Patterson | 47 | 0.04 | 0 |  |  | No |  | Yes | Trickle | Flow from CB3037, CB3035, and CB3033. this survey is for flow from CB3035. Flow coming from sump at CB | No | 0.5 | 0.25 | 0.03 | Unlikely |  | No |  |  | No |  |  | Drain from house is also present in CB. | {C61A9C7D-F01B-4685-8E8A-A44803AC282E} | other | No manhole drains to CB, this is just a house drain |  | -71.438 | 42.5903
110 | 9151e928-66f3-4394-95db-963123fdc1f2 | 2024-04-17 13:42 | LaurynPatterson | 2024-04-17 13:42 | LaurynPatterson | OF_308 | Fletcher Road | 3034 | Beaver Dam Drive | Yes | Yes | 2024-04-17 13:07 | other | Lauryn Patterson | 47 | 0.04 | 0 |  |  | No |  | Yes | Moderate | Flow from CB3037, CB3035, and CB3033. this survey is for flow from CB3033 | No | 0.25 | 0.25 | 0 | Unlikely |  | No |  |  | No |  |  | Drain from house is also present in CB. | {C61A9C7D-F01B-4685-8E8A-A44803AC282E} | other | No manhole drains to CB, this is just a house drain |  | -71.438 | 42.5903
111 | b29dc654-1341-4ae5-85e9-6d61c6075064 | 2024-04-17 13:58 | LaurynPatterson | 2024-04-17 16:00 | LaurynPatterson | OF_469 | Hyacinth Drive | 2906 | Hyacinth Drive | Yes | Yes | 2024-04-17 13:56 | other | Lauryn Patterson | 50 | 0.04 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | No flow present at structure | {20EFBB65-9C92-48B9-93B4-44430D7F88DC} |  |  |  | -71.4512 | 42.5918
112 | ac654c90-3abd-4fa4-8588-5899dc1ba939 | 2024-04-17 16:00 | LaurynPatterson | 2024-04-17 16:00 | LaurynPatterson | OF_222 | Acton Road | 5641 | Acton Road | Yes | Yes | 2024-04-17 15:00 | other | Lauryn Patterson | 50 | 0.04 | 0 |  |  | Partially | Incoming pipe from BMP, no flow at BMP. | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {1A51D25C-8448-4C4B-ABBB-88E8160D0C3C} | No |  |  | -71.3945 | 42.5446
113 | 028b2e2f-c468-4ff3-9af3-7dcd0945fa86 | 2024-04-17 16:00 | LaurynPatterson | 2024-04-22 00:12 | EOlsonTB | Unmapped OF 2 | Misty Lane | 4383 | Misty Lane | Yes | Yes | 2024-04-17 15:24 | other | Lauryn Patterson | 60 | 0.04 | 0 |  |  | Partially | Pipe from CB4384, no flow at CB. | Yes | Trickle | Flow from DMH4379 and 4387. Could not sample from DMH4379 pipe due to depth being greater than sampling pole and the upstream manhole did not have flow. | No | 0.5 | 0 | 0.1 | Unlikely |  | No |  |  | No |  |  | Could not sample from DMH4379 pipe due to depth being greater than sampling pole and the upstream manhole did not have flow. | {8D743CBA-48A9-4E33-8DDC-684B3D22427D} |  |  |  | -71.4122 | 42.5567
114 | 68ff7013-f7fd-4b7f-bbe0-c124d43f497f | 2024-04-17 16:00 | LaurynPatterson | 2024-05-28 18:43 | EOlsonTB | Unmapped OF 2 | Misty Lane | 4390 | Misty Lane | No | No | 2024-04-17 15:44 | other | Lauryn Patterson | 60 | 0.04 | 0 |  |  | Partially | Pipe from CB4389, no flow at CB. | Yes | Moderate | Flow from DMH 4392 | No | 0.5 | 0 | 0.02 | Unlikely |  | No |  |  | No |  |  |  | {A6AAB66C-4182-4BCC-84E4-345CC6F61986} | No |  |  | -71.4122 | 42.5574
115 | f98c7025-95cb-47ca-a55f-fb3ece61c943 | 2024-04-24 12:37 | LaurynPatterson | 2024-05-03 19:20 | EOlsonTB | OF_179 | Misty Lane | 3970 | Misty Lane | Yes | Yes | 2024-04-24 12:05 | other | Lauryn Patterson | 46 | 0 | 0 |  |  | No |  | Yes | Trickle | Flow from DMH 3972, CB 3969, and DMH 3968. This survey is for flow from DMH 3972. | No | 0.5 | 0 | 0.06 | Unlikely |  | No |  |  | No |  |  |  | {1C938941-43F7-40A1-9B9F-2A136B70D8B9} | other | Add in drainage pipes. |  | -71.4146 | 42.5578
116 | 1900305b-2ba0-4a8f-b105-a3748ff95af4 | 2024-04-24 12:39 | LaurynPatterson | 2024-05-03 19:20 | EOlsonTB | OF_179 | Misty Lane | 3970 | Misty Lane | Yes | Yes | 2024-04-24 12:05 | other | Lauryn Patterson | 46 | 0 | 0 |  |  | No |  | Yes | Trickle | Flow from DMH 3972, CB 3969, and DMH 3968. This survey is for flow from CB3969. | No | 0.25 | 0 | 0.01 | Unlikely |  | No |  |  | No |  |  |  | {1C938941-43F7-40A1-9B9F-2A136B70D8B9} | other | Add in drainage pipes. |  | -71.4146 | 42.5578
117 | 615cd8f9-d264-411e-8368-796121cfed9b | 2024-04-24 12:52 | LaurynPatterson | 2024-05-03 19:21 | EOlsonTB | OF_179 | Misty Lane | 3970 | Misty Lane | Yes | Yes | 2024-04-24 12:05 | other | Lauryn Patterson | 46 | 0 | 0 |  |  | No |  | Yes | Trickle | Flow from DMH 3972, CB 3969, and DMH 3968. This survey is for flow from DMH3968 | No | 0.75 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  |  | {1C938941-43F7-40A1-9B9F-2A136B70D8B9} | other | Add in drainage pipes. |  | -71.4146 | 42.5578
118 | 39756211-035b-4ece-854c-d75a7b08aca9 | 2024-04-24 13:27 | LaurynPatterson | 2024-05-28 18:43 | EOlsonTB | OF_179 | Misty Lane | 3975 | Misty Lane | No | No | 2024-04-24 13:05 | other | Lauryn Patterson | 48 | 0 | 0 |  |  | No |  | Yes | Trickle | Flow from DMH 3977 | No | 0.25 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  |  | {C8F3539F-2CA3-4BF5-997E-D3720EC5ABA1} | other |  |  | -71.4144 | 42.5584
119 | 8a2432c2-0b4d-4fa2-bd64-9c3ec4ab75b9 | 2024-04-24 14:15 | LaurynPatterson | 2024-04-24 14:15 | LaurynPatterson | OF_229 | Colonial Drive | 4431 | Colonial Drive | Yes | Yes | 2024-04-24 14:12 | other | Lauryn Patterson | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | KJMH dry. | {A6871A62-D305-4C25-AAC8-91CC6D6A5352} | other | DMH 4432 connects to DMH 4431 |  | -71.3992 | 42.5458
120 | 4c1000d3-4775-4f07-bee0-f2f137e7be00 | 2024-04-24 15:00 | LaurynPatterson | 2024-04-24 15:00 | LaurynPatterson | OF_430 | Magnolia Drive | 4556 | Magnolia Drive | Yes | Yes | 2024-04-24 14:57 | other | Lauryn Patterson | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | Some sheen in standing water present in sump. DMH dry. | {30DC912A-A33D-4E29-95B4-65025472B0A2} | No |  |  | -71.4663 | 42.5602
121 | 7170bd27-4c4f-441e-8398-1bb6fd1bf0df | 2024-04-24 15:35 | LaurynPatterson | 2024-05-28 18:43 | EOlsonTB | OF_409 | Alcorn Crossing | 1810 | Alcorn Crossing | Yes | Yes | 2024-04-24 15:08 | other | Lauryn Patterson | 50 | 0 | 0 |  |  | Fully | Inlet and put,eat pipes in basin. | No |  |  |  | 0.25 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  | Sampled at CB1811 flow from house 22 Alcorn crossing | {D345A2C3-5CB6-4B16-AF48-2EF596E90646} | No |  | Photo 1 is of KJCB inlet and outlet pipes are almost fully submerged. Photo 2 is of upstream CB 1811. Pipe going to KJCB was partially submerged but flow was present coming from pipe leaving 22 Alcorn Crossing. | -71.446 | 42.5741
122 | e2f3e7e7-0a1b-4112-afcd-2627960af9d2 | 2024-04-24 15:49 | LaurynPatterson | 2024-04-24 15:49 | LaurynPatterson | OF_421 | Indigo Lane | 4135 | Indigo Lane | Yes | Yes | 2024-04-24 15:46 | other | Lauryn Patterson | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | KJMH is dry. | {48139B58-9AE9-4A49-B2FE-9D452BFA5C2C} | other | DMH drains to detention basin at end of indigo lane |  | -71.4657 | 42.5554
123 | 71b96d1c-7316-4ec0-b4e4-0a9904dd7376 | 2024-04-24 16:19 | LaurynPatterson | 2024-05-03 19:04 | EOlsonTB | Unmapped OF 6 | North Street | Unmapped DMH | 30 North St | Yes | Yes | 2024-04-24 16:12 | other | Lauryn Patterson | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  |  | other | Update based on as built plans |  | -71.4666 | 42.6014
124 | 0b351d38-9c3f-4985-8c60-4a254711322f | 2024-04-26 12:26 | LaurynPatterson | 2024-04-26 12:26 | LaurynPatterson | OF_266 | Forge Village Road | Unmapped CB | Intersection of Flagg x Forge Village | Yes | Yes | 2024-04-26 12:03 | other | Lauryn Patterson | 40 | 0.01 | 0.01 |  |  | No |  | Yes | Moderate | Flow from unmapped catchbasin to east of DMH. | No | 0.25 | 0 | 0.01 | Unlikely |  | No |  |  | No |  |  |  |  | other | Refer to town provided record drawings. |  | -71.4485 | 42.5794
125 | 57767c3d-e0f8-40ff-b502-5ee66d173d5f | 2024-04-26 12:33 | LaurynPatterson | 2024-04-26 12:33 | LaurynPatterson | OF_266 | Forge Village Road | Unmapped CB | Intersection of Flagg x Forge Village | Yes | Yes | 2024-04-26 12:03 | other | Lauryn Patterson | 40 | 0.01 | 0.01 |  |  | No |  | Yes | Moderate | Flow from unmapped manhole to South of DMH | No | 0.25 | 0.25 | 0.02 | Unlikely |  | No |  |  | No |  |  |  |  | other | Refer to town provided record drawings. |  | -71.4485 | 42.5794
126 | 70496703-4fe5-4414-811f-d9784352811d | 2024-04-26 13:24 | LaurynPatterson | 2024-05-03 19:37 | EOlsonTB | Unmapped OF 3 | Deer Run Dr | 0572 | Main Street | Yes | Yes | 2024-04-26 13:01 | other | Lauryn Patterson | 45 | 0.01 | 0.02 |  |  | No |  | Yes | Moderate | 8” PVC from 180 Main Street house | No | 0.25 | 0 | 0.04 | Unlikely |  | No |  |  | No |  |  |  | {64F4E332-511B-49A4-AEDD-0523EA37FF14} | other | Refer to map book markups |  | -71.407 | 42.5953
127 | 9a4b5c7c-dfe0-43f9-892e-e3cd660c3e0a | 2024-04-26 13:33 | LaurynPatterson | 2024-04-26 13:33 | LaurynPatterson | OF_266 | Forge Village Road | Unmapped CB | Intersection of Flagg x Forge Village | Yes | Yes | 2024-04-26 12:03 | other | Lauryn Patterson | 40 | 0.01 | 0.01 |  |  | No |  | Yes | Moderate | Flow from manhole 4742 | No | 0.25 | 0 | 0 | Unlikely |  | No |  |  | No |  |  |  |  | other | Refer to town provided record drawings. |  | -71.4485 | 42.5794
128 | 1f781076-3ceb-460d-b2b8-ed37cea509ba | 2024-04-26 17:55 | LaurynPatterson | 2024-05-03 19:29 | EOlsonTB | UNK-67 | Cherry Lane | 3931 | Cherry Lane | Yes | Yes | 2024-04-26 17:45 | other | Lauryn Patterson | 55 | 0.01 | 0.01 |  |  | Partially | Incoming pipe from 4818, which was confirmed as no flow | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {69093D10-BF7E-44EB-A19D-E0B7C77903F2} | other | Refer to field work markups done by town |  | -71.4478 | 42.6146
129 | 8422cfd6-d965-4fca-aa6e-02679d23398d | 2024-05-02 12:11 | EMitchellTB | 2024-05-02 12:11 | EMitchellTB | OF-41 | Mitchell Way | 3086 | Mitchell Way | Yes | No? | 2024-05-02 11:58 | Elizabeth Mitchell |  | 50 | 0 | 0 |  |  | No |  | Yes | Trickle | Unmapped pipe | No | 0.25 | 0 | 0.03 | Unlikely |  | No |  |  | No |  |  |  | {745C5242-C9B5-4B4A-8FB1-6A4797BC606D} | other | See map book |  | -71.4325 | 42.6413
130 | 4924ebd7-4da5-4bd1-a096-971622a22bd3 | 2024-05-02 12:34 | EMitchellTB | 2024-05-10 12:52 | EOlsonTB | OF-12 | Dunstable Road | 0610 | Dunstable Road | No | No | 2024-05-02 12:29 | Elizabeth Mitchell |  | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {A4E1F504-3AB6-4A5E-8121-BB5934C6D929} | other |  | See data issue layer / field mapbook. | -71.4588 | 42.6217
131 | 9f5b1510-a64c-4a68-ac19-b8af29bf1c71 | 2024-05-02 13:02 | EMitchellTB | 2024-05-10 19:02 | EOlsonTB | OF-5 | Pond Road | 0602 | Dunstable Road | Yes | No | 2024-05-02 12:41 | Elizabeth Mitchell |  | 50 | 0 | 0 |  |  | No |  | Yes | Trickle | DL-2166 and unmapped pipe across from outlet | No | 0.25 | 0 | 0.01 | Unlikely |  | No |  |  | No |  |  | Unmapped pipe: C=0.00, A=0.00, S=0.25 | {08765777-9269-46F2-B05D-AA0A4EB7145E} | other | Unmapped 15” RCP |  | -71.4561 | 42.6182
132 | 3d173239-bc1f-457f-bf8c-b58da239e92d | 2024-05-02 13:19 | EMitchellTB | 2024-05-02 13:19 | EMitchellTB | OF-346 | Groton Road | 0638 | Groton Road | No | No | 2024-05-02 13:17 | Elizabeth Mitchell |  | 50 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {A16B3482-2692-4156-B373-EECF40A8D128} | other | See map book |  | -71.4436 | 42.6189
133 | e8ccd634-1b5d-464c-abe0-690649e7fe4d | 2024-05-02 14:29 | EMitchellTB | 2024-05-02 14:29 | EMitchellTB | OF-1092 | Plain Road | 0776 | Depot Street | Yes | Yes | 2024-05-02 14:14 | Elizabeth Mitchell |  | 55 | 0 | 0 |  |  | No |  | Yes | Moderate | Upstream catchment | No | 0.25 | 0 | 0 | Unlikely |  | No |  |  | No |  |  |  | {A4B3356C-62B0-4FFB-B63E-6FA8ED74827D} | other | See map book |  | -71.4367 | 42.5947
134 | 82baf1f3-9a10-4dd4-91a5-d10c6c1f82ac | 2024-05-02 14:56 | EMitchellTB | 2024-05-10 19:02 | EOlsonTB | OF-1092 | Plain Road | 0742 | Depot Street | Yes | Yes | 2024-05-02 14:32 | Elizabeth Mitchell |  | 55 | 0 | 0 |  |  | No |  | Yes | Moderate | DL-1106 (in survey), DL-1108 | No | 0.25 | 0 | 0.05 | Unlikely |  | No |  |  | No |  |  | DL-1108: S=0.25, C=0.00, A=0.00 | {5C093307-E1B9-4790-A48D-D4F24BC4DAE3} | No |  |  | -71.4355 | 42.5938
135 | 4564d2f9-d6f5-47f9-b6a9-ba597d6caba7 | 2024-05-02 16:13 | EMitchellTB | 2024-05-10 19:03 | EOlsonTB | OF-231B | Mark Vincent Drive | 4444 | Mark Vincent Drive | Yes | Yes | 2024-05-02 15:38 | Elizabeth Mitchell |  | 60 | 0 | 0 | Structure_damage/corrosion |  | No |  | Yes | Trickle | DL-587, DL-3046 (in survey), DL-591 | No | 0.25 | 0 | 0 | Unlikely |  | No |  |  | No |  |  | DL-591: C=0.01, S=0.25, A=0.00 DL-587: C=0.02, S=0.25, A=0.00 DL-3057 is corroded. Forgot to take photo. | {E56FBE88-45BE-4650-9304-703F7EA02F19} | other |  |  | -71.3973 | 42.5482
136 | 3e408ed7-a281-4eb8-ab81-f261655bfbd6 | 2024-05-03 12:27 | EvelynMortimer | 2024-05-13 12:30 | EOlsonTB | OF_34 | Mitchell Way | 3295 | Mitchell Way | Yes | No | 2024-05-03 12:18 | other | ERM | 45 | 0 | 0 |  |  | No |  | No | [15 empty] | {AAC382AF-DA9F-4CE9-92C2-C30F0E3D90AF} | No |  |  | -71.4303 | 42.6409
137 | b6c5aa11-52a8-477d-a7d6-ea897968559c | 2024-05-03 13:09 | EvelynMortimer | 2024-05-07 13:09 | EOlsonTB | OF_1040 | Links Rd | 1441 | Links Rd | Yes | No | 2024-05-03 13:07 | other | ERM | 45 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely | [8 empty] | {9EBA3DC3-F7FA-4B8D-A39F-FDC6F1F8BAD6} | No |  |  | -71.4119 | 42.6219
138 | dc115441-cf12-423b-b35d-1755439c2f4a | 2024-05-03 13:28 | EvelynMortimer | 2024-05-07 13:08 | EOlsonTB | OF_290 | Kirsi Cir | 2820 | Kirsi Cir | Yes | Yes | 2024-05-03 13:26 | other | ERM | 45 | 0 | 0 |  |  | No |  | No | [15 empty] | {39286029-5458-47CD-9EB6-4AF651F7F6B2} | No |  |  | -71.4199 | 42.5908
139 | a4dfa1c8-b190-46ea-bc38-23886ee8bdec | 2024-05-03 16:26 | EvelynMortimer | 2024-05-28 18:42 | EOlsonTB | OF_212 | Vose Hill Rd | 1926 | Vose Hill Rd | Yes | No | 2024-05-03 15:55 | other | ERM | 50 | 0 | 0 |  |  | No |  | Yes | Trickle | Unmapped 12” HDPE pipe from CB off sidewalk | No | 0.25 | 0.25 | 0 | Unlikely |  | No |  |  | No |  |  |  | {C6080B32-7484-488D-A11E-E99F7F69DF68} | other | New CB off sidewalk |  | -71.3903 | 42.5393
140 | b0896e74-2c36-43c5-8eaf-117b06f42b41 | 2024-05-06 12:03 | LaurynPatterson | 2024-05-06 12:03 | LaurynPatterson | Unmapped OF-3 | Deer Run Dr | 0572 | Main Street | Yes | Yes | 2024-04-26 13:01 | other | Lauryn Patterson | 45 | 0.01 | 0.02 |  |  | No |  | Yes | Moderate | Flow from DMH4742. Sampled at KJMH. | No | 0.25 | 0 | 0 | Unlikely |  | No |  |  | No |  |  |  | 64f4e332-511b-49a4-aedd-0523ea37ff14 | other | Refer to map book markups. |  | 0 | 0
141 | 2f834f9d-e7c7-4124-8726-1da86b5c14ed | 2024-05-06 12:14 | LaurynPatterson | 2024-05-07 13:05 | EOlsonTB | OF_179 | Misty Lane | 3968 | Misty Lane | No | No | 2024-04-26 12:12 | other | Lauryn Patterson | 46 | 0 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | DMH was dry. No flow present. | 2bb50473-a0a9-491e-9bc9-db2b0930d07b | other | Refer to mapbook markups. |  | 0 | 0
142 | e184aaef-8de6-4690-9701-bc51c96740df | 2024-05-10 12:13 | LaurynPatterson | 2024-05-10 12:13 | LaurynPatterson | OF_16 | Wilson Farm Road | 4349 | Wilson Farm Road | Yes | Yes | 2024-05-10 12:05 | other | Lauryn Patterson | 50 | 0.19 | 0 |  |  | Partially | Pipe 3951 | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {FEB11779-C7EE-4C52-B953-F31CED248823} | other | Update pipe flow direction based on mapbook. |  | -71.4176 | 42.5564
143 | e59a137f-a92c-4187-a6b1-578d8c013238 | 2024-05-10 12:38 | LaurynPatterson | 2024-05-28 18:42 | EOlsonTB | OF_16 | Wilson Farm Road | 4353 | Wilson Farm Road | No | No | 2024-05-10 12:17 | other | Lauryn Patterson | 50 | 0.19 | 0 |  |  | No |  | Yes | Trickle | DMH 4354 | No | 0.25 | 0.25 | 0.05 | Unlikely | Sampled here due to the KJMH 4349 and DMH4351 being partially submerged. | No |  |  | No |  |  |  | {B303FA48-1DCB-4025-84D5-00C6247C5ED8} | other | Significant mapping changes needed for this street. Refer to mapbook markups. |  | -71.4171 | 42.5558
144 | 6cbfb85a-6ab6-4add-9284-221188e4f8c9 | 2024-05-10 13:28 | LaurynPatterson | 2024-05-10 13:28 | LaurynPatterson | UNK-59 | Kylemore drive | 2071 | Kylemore Drive | Yes | Yes | 2024-05-10 13:26 | other | Lauryn Patterson | 50 | 0.19 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {4334894E-D754-426B-82F9-E96832D6E7B6} | No |  |  | -71.4688 | 42.5878
145 | 66213162-5d28-4313-8a24-e62fc0d2123c | 2024-05-10 14:01 | LaurynPatterson | 2024-05-10 14:01 | LaurynPatterson | OF_369 | Patriot Lane | 3005 | Patriot Lane | Yes | Yes | 2024-05-10 13:59 | other | Lauryn Patterson | 55 | 0.19 | 0 | Structure_damage/corrosion |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {CD68A35C-D9E6-4CF4-8836-5BA60BF930C9} | other | Refer to mapbook. |  | -71.4498 | 42.5812
146 | 5e78ac22-1f36-4f15-a73a-64722cc44efc | 2024-05-10 14:22 | LaurynPatterson | 2024-05-12 21:12 | EOlsonTB | OF_18 | Wilson Farm Rd | 4345 | Wilson Farm Rd | Yes | Yes | 2024-05-10 14:19 | other | Lauryn Patterson | 55 | 0.19 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {1E822303-A89C-412E-B8A5-2E46AFF232BC} | other | Refer to mapbook |  | -71.4193 | 42.5573
147 | 0a0239f2-522d-4ddc-b965-c848707ab37b | 2024-05-10 14:29 | LaurynPatterson | 2024-05-12 21:40 | EOlsonTB | OF_18 | Wilson Farm Road | 4346 | Wilson Farm Road | No | No | 2024-05-10 14:27 | other | Lauryn Patterson | 55 | 0.19 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {AB68EA4E-8690-42DF-86F7-243B2883BC5A} | other |  |  | -71.4187 | 42.5572
148 | 5fe95d88-8e9e-4f3d-a7b5-b1acc0657564 | 2024-05-10 14:51 | LaurynPatterson | 2024-05-10 14:51 | LaurynPatterson | OF_397 | Annie Place | 2006 | Annie Place | Yes | Yes | 2024-05-10 14:47 | other | Lauryn Patterson | 55 | 0.19 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {0ADC10DE-E639-45DE-8561-CBA019824F03} | No |  |  | -71.3913 | 42.5484
149 | 1dcbb234-1919-4887-a9aa-5a9af16d71dd | 2024-05-10 17:00 | LaurynPatterson | 2024-05-28 18:42 | EOlsonTB | OF_455 | Swedes Crossing | 2537 | Swedes Crossing | No | No | 2024-05-10 16:17 | other | Lauryn Patterson | 60 | 0.19 | 0 |  |  | No |  | Yes | Substantial | Pipe GIS ID 1241 | No | 0.25 | 0.25 | 0.34 | Unlikely |  | No |  |  | No |  |  |  | {D68436AC-3BF7-4071-A31C-54C9E613CD32} | other | Refer to mapbook |  | -71.4121 | 42.5958
150 | 03a116c8-9315-4712-97e9-271cb213cba9 | 2024-05-10 17:00 | LaurynPatterson | 2024-05-28 18:42 | EOlsonTB | OF_455 | Swedes Crossing | 2622 | Swedes Crossing | No | No | 2024-05-10 16:44 | other | Lauryn Patterson | 60 | 0.19 | 0 |  |  | No |  | Yes | Moderate | Pipe GIS ID 1237 | No | 0.25 | 0.25 | 0.12 | Unlikely |  | No |  |  | No |  |  |  | {3DF47187-EF14-41DD-B93A-BDFF1E7795CC} | No |  |  | -71.4121 | 42.5963
151 | f7ecc3bc-5258-4648-95a3-14e14ded348b | 2024-05-21 12:49 | LaurynPatterson | 2024-05-28 18:42 | EOlsonTB | OF_1092 | Depot Street | 0793 | Depot Street | No | No | 2024-05-21 12:35 | other | Lauryn Patterson | 65 | 0.09 | 0 |  |  | No |  | Yes | Trickle | Unmapped manhole in front of Depot Street #33 | No | 0.5 | 0 | 0.05 | Unlikely |  | No |  |  | No |  |  |  | {C8C56097-5220-47F1-8656-CE92A7780314} | other | Refer to map book markups |  | -71.4337 | 42.5917
152 | 9f3b6675-f12a-454b-a94c-6cf608aa593c | 2024-05-21 14:22 | LaurynPatterson | 2024-05-21 14:22 | LaurynPatterson | OF_1092 | Depot Street | 0798 | Depot Street | No | No | 2024-05-21 14:19 | other | Lauryn Patterson | 71 | 0.09 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | Some water leaving manhole from sump. | {FEC88577-E79C-4F40-A2B9-3ED69F7EECC0} | other | Refer to mapbook |  | -71.4333 | 42.5903
153 | 7302bb68-e870-4557-bd0e-e9fc5fef6cc0 | 2024-05-21 14:58 | LaurynPatterson | 2024-05-22 19:03 | EOlsonTB | OF_18 | Wilson Farm Road | Unmapped DMH | Carlisle Road | No | No | 2024-05-21 14:43 | other | Lauryn Patterson | 75 | 0.09 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  | Unmapped manhole that collects drainage from Diane lane and outlets to 5164. No flow present. |  | other | Refer to mapbook |  | -71.4195 | 42.5574
154 | 989b83a7-a285-4eae-a8fe-89d95cca9476 | 2024-05-21 15:15 | LaurynPatterson | 2024-05-21 15:15 | LaurynPatterson | OF_20 | Fieldstone Drive | Unmapped CB | Fieldstone Drive | Yes | Yes | 2024-05-21 14:57 | other | Lauryn Patterson | 74 | 0.09 | 0 |  |  | Partially | Pipe from CB 0861. No flow at upstream | Yes | Trickle | CB0851 | No | 0.25 | 0.25 | 0 | Unlikely |  | No |  |  | No |  |  |  |  | other | Refer to mapbook. |  | -71.4192 | 42.5638
155 | 3c46aad6-ac60-40fe-8b45-1db0474acda1 | 2024-05-21 16:54 | LaurynPatterson | 2024-05-21 16:54 | LaurynPatterson | OF_1005 | Tyngsboro Road | 0580 | Tyngsboro Road | No | No | 2024-05-21 16:38 | other | Lauryn Patterson | 87 | 0.09 | 0 |  |  | No |  | No | [6 empty] | Unlikely |  | No |  |  | No |  |  |  | {1016CFA5-89EC-443C-AF74-C98CA1863C22} | No |  |  | -71.4263 | 42.5959
156 | 782f7657-5e9c-4360-b4ab-dd1f09d79b60 | 2024-05-24 11:23 | LaurynPatterson | 2024-05-28 12:15 | EOlsonTB | OF_18 | Wilson Farm Road | 5570 | Wilson Farm Road | Yes | Yes | 2024-05-21 11:18 | other | Lauryn Patterson | 75 | 0.09 | 0 | other | Manhole is buried | [17 empty] | Unknown condition in the manhole. Could not open the KJMH due to it being buried. Screened the two incoming MHs (MH-4345 and an unmapped manhole) and the downstream MH (MH-4346). | 18456c54-8cf7-4f97-bb1f-d3c408c808c7 | other | Refer to mapbook |  | 0 | 0

## Wet Weather List
| Location | [6 empty] | Laboratory Analysis (1) |  |  |  | Water Quality Meter/Test Kit (1)
Dry Weather Catchment Investigation Status | Date | Time | Outfall ID | Receiving Water | TMDL | Street | Sample Location | Ammonia | Surfactants | E. coli | Total Phosphorus | Temperature | Temperature | Salinity | Conductivity | Chlorine | Ammonia | Dissolved Oxygen
[7 empty] | (Outfall / Upstream MH) | mg/L | mg/L | CFU/100mL | mg/L | oC | oF | ppt | µS/cm (2) | mg/L | mg/L | mg/L
DW catchment investigation completed on 04.16.24 |  |  | OF_10 | Outside Receiving | None | 65 Main St (Roudenbush Community Center)
DW catchment investigation marked as completed on 05.07.24 |  |  | OF_1000 | Outside Receiving | None | 1 Coakley Circle (Stony Brook School)
Need to verify TS |  |  | OF_317 | Outside Receiving | None | 25 Depot St (Abbott School / Millennium School)
Need to verify TS |  |  | OF_317B | Outside Receiving | None | 25 Depot St (Abbott School / Millennium School)
DW catchment investigation completed (no junction, TS confirmed by record planning) on 05.29.24 |  |  | OF_318 | Outside Receiving | None | 25 Depot St (Abbott School / Millennium School)
DW catchment investigation completed on 04.17.24 |  |  | OF_383 | Outside Receiving | None | 4 Stoneview Dr
DW catchment investigation completed on 05.02.24 |  |  | OF_41 | Outside Receiving | None | Vineyard Rd at Mitchell Way (Rita Edwards Miller School)
DW Catchment investigation completed on 12.08.23 |  |  | OF_423 | Outside Receiving | None | 3 Chicory Rd
DW Catchment investigation completed on 04.24.24 |  |  | OF_424 | Outside Receiving | None | 30 Magnolia Rd
No connecting structures mapped. Need to investigate in field. |  |  | OF_83 | Outside Receiving | None | 25 Depot St (Abbott School / Millennium School)
DW investigation N/A - Culvert (no connecting structures, see outfall list tab for more info) |  |  | OF_85 | Outside Receiving | None | 65 Main St (Roudenbush Community Center)
DW Investigation N/A - Culvert (no connecting structures, see outfall list tab for more info) |  |  | OF_86 | Outside Receiving | None | 65 Main St (Roudenbush Community Center)
DW Catchment investigation completed on 12.15.23 |  |  | UNK-56 | Outside Receiving | None | 18 Casie Lane
DW Catchment investigation completed on 04.24.24 |  |  | Unmapped OF 7 | Outside Receiving | None | Magnolia Dr near Greenbier Dr
REPORTING LIMITS Ammonia = 0.075 mg/L Surfactants = 0.050 mg/L E. coli = 2 CFU/100mL Fecal Coliform = 2 CFU/100mL BOD5 = 2 mg/L Total Phosphorus = 0.01 mg/L "ND" = none detected |  |  |  | COLOR KEY (benchmarks are bold)
[5 empty] | Ammonia | Surfactants | E. coli | Total Phosphorus |  | Temperature | Salinity | Conductivity | Chlorine | Ammonia | Dissolved Oxygen
[5 empty] | mg/L | mg/L | CFU/100 mL | mg/L |  | oF | ppt | µS/cm | mg/L | mg/L | mg/L
[5 empty] | 6 | 1 | 10000 | 0.908 |  | 83 | 1 | 2000 | 1 | 6
[5 empty] | 1 | 0.5 | 1260 | 0.466 |  | 83 | 0.75 | 1500 | 0.3 | 1
[5 empty] | 0.5 | 0.25 | 235 | 0.024 |  | 83 | 0.5 | 1000 | 0.02 | 0.5 | 5
[5 empty] | < 0.5 | < 0.25 | < 235 | < 0.024 |  | < 83 | < 0.5 | < 1,000 | < 0.02 | < 0.5 | ≥ 5.0
Notes for Results Summary: |  |  |  | Benchmark Sources:
(1) "-" means no analysis was completed |  |  |  | Ammonia, Surfactants, and Chlorine - EPA General Permit for Stormwater Discharges from Small MS4 in Massachusetts
(2) µS/cm is equivalent to µmhos/cm |  |  |  | E. coli, Temperature, and Dissolved Oxygen - 314 CMR 4.00: Massachusetts Surface Water Quality Standards
(3) analytical method 121,9213D |  |  |  | Fecal coliform - MWRA Water Quality Standards for Class B and Class SB Waters
Total Phosphorus - EPA Ambient Water Quality Criteria Recommendations for Rivers and Streams in Nutrient Ecoregion XIV
Salinity - EPA Volunteer Estuary Monitoring: A Methods Manual
Conductivity - Center for Watershed Protection Illicit discharge Detection and Elimination Guidance Manual
BOD5 has no quantitative benchmark for surface water grab samples
None completed in PY6

## data (hidden)
Catchment Investigation Status | Catchment Priority | Flow Present? | Pool Sampled? | KJMH Complete | Evidence of Potential Illict Connection? | Suspected IDDE? | Structure Type | Wet Weather Status
Visited - Complete | Problem | Yes | Yes |  | Yes | Unlikely | KJMH | Visited - Complete
Revisit | High | No | No |  | No | Potential | Terminal Structure | Revisit - No Rain
Not Applicable | Low |  |  |  |  | Suspect | Manhole | Not Applicable
[6 empty] | Obvious | Catchbasin